## Sprint Summary Q1
Sprint ends on or before | 2020-01-03 | 2020-01-17 | 2020-01-31 | 2020-02-14 | 2020-02-28 | 2020-03-13 | 2020-03-27 | Total Q1 | Promises Kept Q1
Predictablity - Sprint Completion
Originally Planned PBIs or Bugs Completed |  | 18 | 43 | 42 | 35 | 65 | 23 | 226
Originally Planned PBIs or Bugs Not Completed |  | 15 | 8 | 0 | 3 | 1 | 7 | 34
Sprint Forecast Completion Percentage |  | 54.55% | 84.31% | 100% | 92.11% | 98.48% | 76.67% | 84.35% | 16.67%
Add On PBIs or Bugs Completed |  | 4 | 0 | 16 | 8 | 25 | 12 | 65
Reason if sprint not completed - indicate with X
Team Overcommitted | [7 empty] | 0
Unplanned Activity | [7 empty] | 0
Impediment or Dependency |  | X | X |  | X | X | X | 5
Production Issues Significantly Increased | [7 empty] | 0
Other - Indicate with X, then Specify on 'Other' Sheet | [7 empty] | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed |  | 0 | 0 | 0 | 0 | 0 |  | 0 | Run
Support: Production Support PBIs - Completed |  | 0 | 0 | 0 | 0 | 0 |  | 0
New Value: Non-Support PBIs - Completed |  | 15 | 16 | 27 | 35 | 29 | 33 | 155 | Grow
New Value: Bugs Discovered Before Production - Completed |  | 7 | 27 | 31 | 8 | 61 | 2 | 136
New Value: Automation or Innovation PBIs - Completed |  | 0 | 0 | 0 | 0 | 0 |  | 0 | Transform
Total % spent on New Value Creation |  | 68.18% | 37.21% | 46.55% | 81.4% | 32.22% | 94.29% | 59.97%
Continuous Improvement
Concrete Improvements Completed |  | 0 | [5 empty] | 0
Concrete Improvements Not Completed |  | 0 | [5 empty] | 0
Continuous Improvement Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Next: Fill in the "New Value - OTR & ITRs" Sheet

## Sprint Summary Q2
Sprint ends on or before | 2020-04-10 | 2020-04-24 | 2020-05-08 | 2020-05-22 | 2020-06-05 | 2020-06-19 | Total Q2 | Promises Kept Q2
Predictability - Sprint Completion
Originally Planned PBIs or Bugs Completed | 38 | 44 |  |  |  |  | 82
Originally Planned PBIs or Bugs Not Completed | 11 | 6 |  |  |  |  | 17
Sprint Forecast Completion Percentage | 77.55% | 88% | #N/A | #N/A | #N/A | #N/A | 82.78% | 0%
Add On PBIs or Bugs Completed | 8 | 18 |  |  |  |  | 26
Reason if sprint not completed - indicate with X
Team Overcommitted | [6 empty] | 0
Unplanned Activity | [6 empty] | 0
Impediment or Dependency | X | [5 empty] | 1
Production Issues Significantly Increased | [6 empty] | 0
Other - Indicate with X, then Specify on 'Other' Sheet | [6 empty] | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed | 0 | 0 |  |  |  |  | 0 | Run
Support: Production Support PBIs - Completed | 0 | 0 |  |  |  |  | 0
New Value: Non-Support PBIs - Completed | 34 | 35 |  |  |  |  | 69 | Grow
New Value: Bugs Discovered Before Production - Completed | 12 | 27 |  |  |  |  | 39
New Value: Automation or Innovation PBIs - Completed | 0 | [5 empty] | 0 | Transform
Total % spent on New Value Creation | 100% | 100% | #N/A | #N/A | #N/A | #N/A | 100%
Continuous Improvement
Concrete Improvements Completed | [6 empty] | 0
Concrete Improvements Not Completed | [6 empty] | 0
Continuous Improvement Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Next: Fill in the "New Value - OTR & ITRs" Sheet

## Sprint Summary Q3
Sprint ends on or before | 2020-07-03 | 2020-07-17 | 2020-07-31 | 2020-08-14 | 2020-08-28 | 2020-09-11 | 2020-09-25 | Total Q3 | Promises Kept Q3
Predictability - Sprint Completion
Originally Planned PBIs or Bugs Completed
Originally Planned PBIs or Bugs Not Completed
Sprint Forecast Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Add On PBIs or Bugs Completed
Reason if sprint not completed - indicate with X
Team Overcommitted | [7 empty] | 0
Unplanned Activity | [7 empty] | 0
Impediment or Dependency | [7 empty] | 0
Production Issues Significantly Increased | [7 empty] | 0
Other - Indicate with X, then Specify on 'Other' Sheet | [7 empty] | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed | [7 empty] | 0 | Run
Support: Production Support PBIs - Completed | [7 empty] | 0
New Value: Non-Support PBIs - Completed | [7 empty] | 0 | Grow
New Value: Bugs Discovered Before Production - Completed | [7 empty] | 0
New Value: Automation or Innovation PBIs - Completed | [7 empty] | 0 | Transform
Total % spent on New Value Creation | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Continuous Improvement
Concrete Improvements Completed | [7 empty] | 0
Concrete Improvements Not Completed | [7 empty] | 0
Continuous Improvement Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Next: Fill in the "New Value - OTR & ITRs" Sheet

## Sprint Summary Q4
Sprint ends on or before | 2020-10-09 | 2020-10-23 | 2020-11-06 | 2020-11-20 | 2020-12-04 | 2020-12-18 | Total Q4 | Promises Kept Q4
Predictability - Sprint Completion
Originally Planned PBIs or Bugs Completed | [6 empty] | #N/A
Originally Planned PBIs or Bugs Not Completed | [6 empty] | #N/A
Sprint Forecast Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Add On PBIs or Bugs Completed
Reason if sprint not completed - indicate with X
Team Overcommitted | [6 empty] | 0
Unplanned Activity | [6 empty] | 0
Impediment or Dependency | [6 empty] | 0
Production Issues Significantly Increased | [6 empty] | 0
Other - Indicate with X, then Specify on 'Other' Sheet | [6 empty] | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed | [6 empty] | 0 | Run
Support: Production Support PBIs - Completed | [6 empty] | 0
New Value: Non-Support PBIs - Completed | [6 empty] | 0 | Grow
New Value: Bugs Discovered Before Production - Completed | [6 empty] | 0
New Value: Automation or Innovation PBIs - Completed | [6 empty] | 0 | Transform
Total % spent on New Value Creation | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Continuous Improvement
Concrete Improvements Completed | [6 empty] | 0
Concrete Improvements Not Completed | [6 empty] | 0
Continuous Improvement Completion Percentage | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Next: Fill in the "New Value - OTR & ITRs" Sheet

## Other
Sprint Ending on or before | If you indicated 'Other', please specify the reason why the team did not complete the Sprint.
2020-01-03
2020-01-17
2020-01-31
2020-02-14
2020-02-28
2020-03-13
2020-03-27
2020-04-10
2020-04-24
2020-05-08
2020-05-22
2020-06-05
2020-06-19
2020-07-03
2020-07-17
2020-07-31
2020-08-14
2020-08-28
2020-09-11
2020-09-25
2020-10-09
2020-10-23
2020-11-06
2020-11-20
2020-12-04
2020-12-18

## New Value - OTR & ITRs
Sprint Ending on or before | If the team worked on items in the sprint related to an OTR or ITR, list the OTR or ITR number(s) below.
2020-01-03
2020-01-17
2020-01-31
2020-02-14
2020-02-28
2020-03-13
2020-03-27
2020-04-10
2020-04-24
2020-05-08
2020-05-22
2020-06-05
2020-06-19
2020-07-03
2020-07-17
2020-07-31
2020-08-14
2020-08-28
2020-09-11
2020-09-25
2020-10-09
2020-10-23
2020-11-06
2020-11-20
2020-12-04
2020-12-18

## Instructions
Instructions for filling out the Sprint Summary Report
1. Every 2 weeks at the beginning of the Sprint Retrospective, the team fills out the Sprint Summary Report with the Scrum Master facilitating.
Note: The entire team is involved in filling out the report to help build team ownership.
Questions and Answers
Due Date?
If for some reason the report is not completed during the Sprint Retrospective, this report is due by Close-of-Business (COB) the day after Sprint Planning.
Do I need to submit or email the report?
No. You only need to fill it out on the shared drive.
The report is located at M:\Technology\Application\Sprint Summary Reports
What is the purpose of this report?
1. To help the team improve itself.
2. To improve our predictability to the business.
3. To increase focus on New Value Creation, as appropriate.
4. To encourage the team to consistently make continuous improvements.
5. To be able to communicate our overall progress and improvements to the business.
How do I count the "Originally Planned PBIs or Bugs Completed?"
Total up the number of PBIs or Bugs that were completed in the sprint as defined in your Sprint Planning. A PBI or Bug may be counted as completed for the sprint even if it is not closed. For example, if the goal of the sprint for a bug was to fix the bug and have it tested in ARDEV, then the bug is counted as complete for the Sprint, even though the bug is not yet closed.
How do I count bugs found during a Sprint that are related to a PBI in that Sprint?
When a PBI is planned into a sprint, the team also plans some time to fix bugs related to the PBI that may be discovered during the sprint as a result of initial testing. These bugs are counted as "Originally Planned" even though they will be entered during the sprint as they are found.
How do I count the "Originally Planned PBIs or Bugs Not Completed?"
Total up the number of PBIs or Bugs that were not completed during the Sprint, yet were originally committed to by the team during Sprint Planning to be "completed."
How can I track whether a PBI or Bug was not completed in the sprint?
Teams can add a simple indicator to the beginning title of a PBI or Bug, such as [S12] for Sprint 12. When the bug is planned into a future sprint, this indicator in the title tells the team the PBI or Bug was started yet not completed in Sprint 12. The indicator makes it easier to count how many items were not completed during the previous sprint.
How do I count "Add On PBIs or Bugs Completed"
Total the number of any additional PBIs or Bugs that were not originally planned in Sprint Planning that were completed during the sprint. For example, if a team member gets to the end of a sprint and cannot help out other team members on PBIs or Bugs in the sprint, then they may take a PBI or Bug from the top of the Product Backlog as an "Add On" to the Sprint. If they complete the Add On during the sprint, it is counted as an Add On. Note: The Product Owner is made aware of any Add Ons to the Sprint. An indicator is also added to the beginning title of the PBI or Bug of "[Add on]" so the team can easily identify Add Ons.
Why are Add Ons not included in the Sprint Forecast Completion Percentage and Promises Kept?
Because Add Ons were not originally committed to during Sprint Planning, they are not counted in these percentages. Also, we want the teams to focus on completing their originally committed items in the sprint and achieving 100% sprint completion.
What if the team started on an Add On PBI or Bug, yet didn't complete it in the sprint?
This is perfectly acceptable and it gives the team a head start on the PBI or Bug for the next sprint. Any Add Ons not completed are moved back to the Prioritized Product Backlog to be considered for a future sprint. As mentioned above, if an Add On was not completed, this does not affect the Sprint Forecast Completion Percentage or Promises Kept percentages. Also, for Add Ons not completed in a sprint, you do not add the Sprint indicator to the title, for example [S12] because Add Ons were not committed to in that sprint.
How is the Promises Kept percentage calculated?
Promises Kept are calculated by determining how many sprints were completed, meaning completing 100% of the items the team originally committed to during Sprint Planning. For example, if the team completed 5 out of the 6 sprints by achieving 100% Sprint Completion in 5 sprints, then Promises Kept is 83%, or 5 divided by 6.
What is a good goal for Promises Kept?
A good goal is 80% or above. An important note is the goal for Promises Kept is not for the team to always achieve 100%, as this may cause the team to be overly cautious and not take some risks. On the other hand, we do not want teams to purposely miss completing their sprint either. A good goal would be if a team completes 5 out of every 6 sprints.
Can I select multiple reasons why a Sprint was not completed 100%?
Yes.
Where do I specify the "Other" reason?
Click on the "Other" sheet and type in the reason next to the corresponding sprint.
How do I fill in "Support vs. New Value Creation?"
You categorize all PBIs and/or Bugs that were completed during the sprint into one of these 5 categories. The total items you have listed in "Support vs. New Value Creation" should equal the total completed items in rows 3 and 6.
What are "automation or innovation PBIs?"
They are PBIs that are working towards automating manual processes or doing some sort of innovation work or initiative. Note: Automated System Tests are not counted under this category as these are tasks under PBI's and are expected to be automated as appropriate. If you have any questions whether a PBI falls under automation or innovation, please ask your Architect or IT Manager.
What is Run, Grow, and Transform?
It is another categorization similar to Support vs. New Value Creation. Run is for support items and the work needed to keep the existing applications and infrastructure up and running, including fixing of bugs found in Production. Grow is non-support work, such as work towards OTRs, ITRs, project work, initiatives, new enhancements, new features, or new applications. Transform is for PBIs that work on automation or innovation initiatives.
How are Continuous Improvements determined?
As a result of the Sprint Retrospective, the team adds any Concrete Improvement(s) they plan to complete as a PBI(s) in the next sprint. A Concrete Improvement may be just a small step towards making the actual improvement, such as having an initial meeting to discuss a change. If the team completes the Concrete Improvement during the sprint, then it is counted, even if the Concrete Improvement was something done outside of the team.
How do you indicate if a PBI is a Concrete Improvement?
At the beginning of the title of the PBI you add "CI:" and then add the description.
Do Concrete Improvements count towards or against the Sprint Completion or Promises Kept percentages?
No. Concrete Improvements do not factor into these percentages and it has its own percentage completion.
What if the team did not plan any Concrete Improvements in the last sprint?
Enter 0 into the fields. Note: The percentage for that sprint will not display as 0, which is correct.
How do I fill in the "New Value - OTR & ITRs" sheet?
Click on the sheet "New Value - OTR & ITRs." If any PBIs during the last sprint are related to an OTR or ITR, enter the OTR or ITR number so we can create a summary report of OTRs and ITRs being worked.

## Sprint Summary YTD
Sprint ends on or before | Total Q2 | Promises Kept Q2 | Total Q3 | Promises Kept Q3 | Total Q4 | Promises Kept Q4 | Total YTD | Promises Kept YTD
Predictability - Sprint Completion
Originally Planned PBIs or Bugs Completed | #REF! |  |  |  | #N/A |  | 82
Originally Planned PBIs or Bugs Not Completed | #REF! |  |  |  | #N/A |  | 17
Sprint Forecast Completion Percentage | #REF! | 82.78% | #N/A | #N/A | #N/A | #N/A | 82.78% | 0%
Add On PBIs or Bugs Completed | #REF! | [5 empty] | 26
Reason if sprint not completed - indicate with X
Team Overcommitted | 0 |  | 0 |  | 0 |  | 0
Unplanned Activity | 0 |  | 0 |  | 0 |  | 0
Impediment or Dependency | 1 |  | 0 |  | 0 |  | 1
Production Issues Significantly Increased | 0 |  | 0 |  | 0 |  | 0
Other - Indicate with X, then Specify on 'Other' Sheet | 0 |  | 0 |  | 0 |  | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed | 0 |  | 0 |  | 0 |  | #REF! | Run
Support: Production Support PBIs - Completed | 0 |  | 0 |  | 0 |  | #REF!
New Value: Non-Support PBIs - Completed | 69 |  | 0 |  | 0 |  | #REF! | Grow
New Value: Bugs Discovered Before Production - Completed | 39 |  | 0 |  | 0 |  | #REF!
New Value: Automation or Innovation PBIs - Completed | 0 |  | 0 |  | 0 |  | #REF! | Transform
Total % spent on New Value Creation | 100% |  | #N/A |  | #N/A |  | 100%
Continuous Improvement
Concrete Improvements Completed | 0 |  | 0 |  | 0 |  | #REF!
Concrete Improvements Not Completed | 0 |  | 0 |  | 0 |  | #REF!
Continuous Improvement Completion Percentage | #N/A |  | #N/A |  | #N/A |  | #N/A

## Calculations
Sprint ends on or before | 2019-01-03 | 2019-01-17 | 2019-01-31 | 2019-02-14 | 2019-02-28 | 2019-03-13 | 2019-03-27 | 2019-04-10 | 2019-04-24 | 2019-05-08 | 2019-05-22 | 2019-06-05 | 2019-06-19 | 2019-07-03 | 2019-07-17 | 2019-07-31 | 2019-08-14 | 2019-08-28 | 2019-09-11 | 2019-09-25 | 2019-10-09 | 2019-10-23 | 2019-11-06 | 2019-11-20 | 2019-12-04 | 2019-12-18 | Year to Date | Promises Kept YTD
Predictability - Sprint Completion
Originally Planned PBIs or Bugs Completed | 0 | 18 | 43 | 42 | 35 | 65 | 23 | 38 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82
Originally Planned PBIs or Bugs Not Completed | 0 | 15 | 8 | 0 | 3 | 1 | 7 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
Sprint Forecast Completion Percentage | [7 empty] | 77.55% | 88% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 82.78% | 0%
Add On PBIs or Bugs Completed | 0 | 4 | 0 | 16 | 8 | 25 | 12 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
Reason if sprint not completed - indicate with X
Team Overcommitted | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Unplanned Activity | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Impediment or Dependency | [7 empty] | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 1
Prod Issues Increased | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Other | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Support vs. New Value Creation
Support: Bugs Found in Production - Completed | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | Run
Support: Production Support PBIs - Completed | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
New Value: Non-Support PBIs - Completed | [7 empty] | 34 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | Grow
New Value: Bugs Discovered Before Production - Completed | [7 empty] | 12 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
New Value: Automation or Innovation PBIs - Completed | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | Transform
Total % spent on New Value Creation | [7 empty] | 100% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 100%
Continuous Improvement
Concrete Improvements Completed | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
Concrete Improvements Not Completed | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
Continuous Improvement Completion Percentage | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Promises Kept by Sprint | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Sprint Completion Q1 - Q4 | 2019-04-10: 1st Quarter; 2019-04-24: 2nd Quarter; 2019-05-08: 3rd Quarter; 2019-05-22: 4th Quarter
Sprint Completion | 2019-04-10: 84.35%; 2019-04-24: 82.78%; 2019-05-08: #N/A; 2019-05-22: #N/A
Promises Kept Q2 - Q4 | 2019-04-10: 1st Quarter; 2019-04-24: 2nd Quarter; 2019-05-08: 3rd Quarter; 2019-05-22: 4th Quarter
Promises Kept | 2019-04-10: 16.67%; 2019-04-24: 82.78%; 2019-05-08: #N/A; 2019-05-22: #N/A
Velocity - Average Completed PBIs or Bugs by Quarter | 2019-07-17: 2nd Quarter; 2019-07-31: 3rd Quarter; 2019-08-14: 4th Quarter
Average Completed PBIs or Bugs by Quarter | 2019-07-17: 13.6667; 2019-07-31: 0; 2019-08-14: 0
Support vs. New Value | 2019-04-10: 1st Quarter; 2019-04-24: 2nd Quarter; 2019-05-08: 3rd Quarter; 2019-05-22: 4th Quarter; 2019-06-05: YTD
Support | 2019-04-10: 40.03%; 2019-04-24: 100%; 2019-05-08: #N/A; 2019-05-22: 100%; 2019-06-05: 0%
New Value | 2019-04-10: 59.97%; 2019-04-24: 0%; 2019-05-08: #N/A; 2019-05-22: 0%; 2019-06-05: 100%
Percentage Change between Quarters | 2019-04-10: 2nd Quarter; 2019-04-24: 3rd Quarter; 2019-05-08: 4th Quarter; 2019-05-22: Q2 - Q4
Sprint Completion | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Promises Kept | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
New Value Created | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Continuous Improvements Completion | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Detailed Breakout of Support vs. New Value Created
Support: Production Bugs | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 0%
Support: Production Support PBIs | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 0%
New Value: Non-Support PBIs | [7 empty] | 73.91% | 56.45% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 65.18%
New Value: Bugs before Production | [7 empty] | 26.09% | 43.55% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 34.82%
New Value: Automation and Innovation | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 0%
Detailed Breakout by Quarter for Support vs. New Value | 2019-04-10: 2nd Quarter; 2019-04-24: 3rd Quarter; 2019-05-08: 4th Quarter; 2019-05-22: YTD
Production Bugs | 2019-04-10: 0%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 0%
Production Support PBIs | 2019-04-10: 0%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 0%
Non-Support PBIs | 2019-04-10: 65.18%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 65.18%
Bugs before Production | 2019-04-10: 34.82%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 34.82%
Automation and Innovation | 2019-04-10: 0%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 0%
Run, Grow, Transform
Run | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 0%
Grow | [7 empty] | 100% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 100%
Transform | [7 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | 0%
Run, Grow, Transform by Quarter | 2019-04-10: 2nd Quarter; 2019-04-24: 3rd Quarter; 2019-05-08: 4th Quarter; 2019-05-22: YTD
Run | 2019-04-10: 0%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 0%
Grow | 2019-04-10: 100%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 100%
Transform | 2019-04-10: 0%; 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: 0%
Percentage Change of Run, Grow, Transform between Quarters | 2019-04-10: 2nd Quarter; 2019-04-24: 3rd Quarter; 2019-05-08: 4th Quarter; 2019-05-22: Q2 - Q4
Run | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Grow | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Transform | 2019-04-24: #N/A; 2019-05-08: #N/A; 2019-05-22: #N/A
Continuous Improvement | 2019-04-10: 2nd Quarter; 2019-04-24: 3rd Quarter; 2019-05-08: 4th Quarter
Continuous Improvement Completion Percentage | 2019-04-10: #N/A; 2019-04-24: #N/A; 2019-05-08: #N/A
Selected Items Completed | 2019-04-10: Q2; 2019-04-24: Q2 + Q3; 2019-05-08: Q2 + Q3 + Q4
Total PBIs and Bugs Completed | 2019-04-10: 108; 2019-04-24: 108; 2019-05-08: 108
New Value PBIs and Bugs Completed | 2019-04-10: 108; 2019-04-24: 108; 2019-05-08: #REF!
Continuous Improvements Completed | 2019-04-10: #REF!; 2019-04-24: #REF!; 2019-05-08: #REF!
Note on A60: Andrew Crookston: Run= Support Grow = New Value Created (except Automation and Innovation) Transform = Automation and Innovation